## Sheet1
Date | Sl. No | Task | Time Needed (hrs) | Estimate Type | Time Taken (hrs) | Status
2025-10-13 | 1 | Make MDI Form | 0h 10m | UI | 0h 10m | Completed
| 2 | Make Single instance of Child Form | 2h 00m | UI | 2h 00m | Completed
| 3 | Set KeyPreview to True and add Esc key code to show message | 1h 15m | UI | 1h 15m | Completed
| 4 | Test all the screens once to confirm KeyPreview set to True | 1h 15m | UI | 1h 15m | Completed
| 5 | Options Title - Added on "Dashboard" Tested for the same Confirmed worked as expected | 2h 00m | UI | 2h 00m | Completed
2025-10-14 | 1 | Employee Self Service - Menu | 2h 30m | UI |  | Need to start
| 2 | Add all associated menus with respect to only ESS
3
4
5